Request For Proposal

Upgrade of the C2 Sector Project Design Documentation

LLC "Primera Golf and Residence" ID: 404481379

PROPOSALS DUE BY: 31.01.2023

Company Background

Tbilisi Hills Golf & Residences is a new and unique residential real estate project in Georgia. A team of professionals, who have created a lot of modern and respectable residential compounds in different countries of Europe participated in its creation.

All nuances of the existing ecosystem and the terrain peculiarities were taken into account. The residential compound has a unique and original image: here the elegant landscape and thought-out comfortable infrastructure were combined. This allows residents of Tbilisi Hills to enjoy all the advantages of owning suburban real estate near the center of the capital.

This is a harmonious unity of the nature of Georgia and audacious architectural solutions. The amount invested so far is more than 33 million euros, which has been devoted to installing the necessary infrastructure for the golf course and the construction of communications. The total cost of the project will be 1 billion euros!

The comprehensive approach of our international team and attention to detail allow me to say without any doubts that Tbilisi Hills corresponds to the highest European standards; everything has been thought out for a harmonious, comfortable, and safe life.

Project Overview

The C2 sector, located on the northern side of the Tbilisi Hills, has a total area of 128,664.0 sq.m. The site has a mountainous terrain with ravines, flora, and fauna. The project development of the C2 sector started last year, in 2022, within the framework of GDG (Detailed Development Plan). The Client commissioned the main road network project and divided the territory into 54 independent land plots according to that project. The Client carried out works for main road corridor construction and excavation according to the main road network design project (attached in Annex 1). However, this design failed to meet the following critical criteria specific to the residential area:

• Accessibility - After incorrect land-cutting and backfilling activities, 10 land plots became inaccessible from the main road level.

• Commercial viability – The land division in Annex 1 design package did not consider naturally sloped, hillside terrain resulting in several land plots placed on a steep slope, potentially overcomplicating residential house construction and reducing the commercial attractiveness of these plots.

• Safety - Steep slope of the road profile and poor planning of the serpentine road resulted in unsafe areas and poor visibility areas for traffic movement. The proximity of the main road to residential plots and land borders, without a buffer space between traffic and private property, resulted in negative potential client feedback and low sales figures.

• Environmental protection – Deep excavation and construction works damaged the earth's rock surfaces and topsoil layers, which require specific conservation to avoid deterioration and erosion.

Due to these and other problems with the main road design package (Annex 1), the Client deemed the continuation of construction works and the development of the C2 sector ineffective and has decided to update the design with a proper urban plan with secondary and access roads, public areas, parking, etc. (as described in Scope of Works).

The construction works will be resumed in parallel to the development of the updated design package. The consultant of this scope should take this into consideration and promptly provide drawings, documents and information for major changes and deviations from existing (old) design that might impact or delay ongoing construction works in any way.

Project Goals

- Create updated urban plan based on the existing main road network design package, taking into account pre-existing conditions and construction works already commenced on the site;

- Design and update secondary roads for individual property access, network connections point for lands and roadside parking areas, considering accessibility, safety, and environmental protection;

- Develop updated multidisciplinary detailed construction design and tender* packages according to the requirements of the Scope of Work.

Critical Remarks to Consider Before and During Planning

- Land plots N8, 12, 13, and 18 in the C2 sector are already sold. The interests of the private owner should be taken into account as much as possible during planning;

- The contractor for the installation of the drainage and sewage network is selected and implementation has started. Proper coordination between design and ongoing works is required;

- The outline contours of existing dirt/gravel roads should be preserved as much as possible;

- The red cadastral lines and areas of existing land plots should be preserved as much as possible;

- Existing road profiles that have been defined for the C2 sector should be maintained.

- Critical and major changes to any part of existing design package should be provided after initial review to be considered during ongoing construction works

- Specific service providers, future residents, and Tbilisi Hills will use main network systems to connect additional networks (e.i. lightning for fences, public green area, up lighting, roadside plant watering systems, resident landscape irrigation, etc.). These connection points and future loads must be considered during planning of any network systems

Scope of Works

The objective of this chapter is to give a clear list of requirements for the development of multidisciplinary, detailed construction design documentation and tender* packages for the C2 sector rehabilitation.

# Update of the existing urban plan for the entire C2 sector

- Study the existing design package (Annex 1) and assess the preexisting road construction works;

- Develop a coherent and detailed action plan for updating the existing urban plan and approve it with the Client;

- Provide urgent design solutions, drawings, and recommendations to the construction team, that might impair the construction process or future design development as part of this scope;

- Improve accessibility of existing roads and networks (develop secondary road scheme, make all land plots accessible from the main road. Road design (width and turn radii) should allow safe and uninterrupted passage for all types of vehicles: cars, SUVs, heavy trucks, service cars, emergency and Fire brigade vehicles, heavy-duty construction vehicles, snow cleaners, accessibility for handicapped visitors and their vehicles, etc.);

- Improve accessibility for pedestrian road network;

- Develop options for environmentally friendly roadside parking lots dedicated to visitor parking considering future demand and traffic loads;

- Develop Special lots for plowing and snow removal (collection);

- Develop traffic accident prevention measures against climate conditions (ice, fog, rain, snow, wind, sun);

- Develop traffic planning and signage (signs; safety barriers, mirrors, etc.);

- Develop special plots for small roadside seating areas (Seating benches, dog stations, garbage bins, etc.);

- Assess and analyze the best use of land plots for the entire C2 sector (potential placement of residential buildings, 3D models showing two-story houses potential allocation on the all-land plots)

- Develop updated vertical planning design for the entire C2 sector.

- Prepare updated GDG package for submission for approval to government institutions

# Redesign of existing landscape design for the entire C2 sector

- Develop landscape restoration management strategy;

- Develop land/rock erosion prevention and repair strategy;

- Design strategic windbreak zones and their arrangement;

- Develop an up-lighting and lighting strategy and placement for roads, sidewalks, roadside, parking areas, roadside areas, walkways, etc.;

- Develop street light design;

# Redesign and update of existing utility and communication network for the entire C2 sector

- Assess existing network schemes and available network loads for connecting the C2 sector;

- Develop storm and rainwater management systems and strategies (this should include temporary rainwater and drainage management systems, to operate during the construction process and work with temporary asphalt road covers);

- Develop sewage and sewerage water management systems and strategies;

- Designate a special plot(s) and design pump stations for any network system that requires pumping (el. Power generators for pumps must be considered for power outages);

- Develop an electrical network project and designate a special plot(s) for el. cabinet allocation for the entire area;

- Develop street light and lamp post arrangements;

- Designate an alternative special plot(s) for electrical meter allocation for all residents;

- Designate an alternative special plot(s) for gas meter allocation for all residents;

- Redesign a fire safety and hydrant network for the entire area (if necessary).

- Provide all network availability and connection points from central network systems to individual land plots (plumbing, sewage, sewerage, drainage, irrigation, electricity, internet, etc.);

- Provide updated connection points, scheme and load calculation and for all network and their connection to existing main networks outside C2 (plumbing, sewage, sewerage, drainage, irrigation, electricity, internet, etc.);

Target Deliverable Schedule

| Phases: |  | Schedule: |
| --- | --- | --- |
| I | Concept design development: Part I Assessment of existing project and site conditions, considering existing network systems and their loads for connecting the C2 networks and development of coherent design and action plan, and approval with the Client Provide urgent design solutions, drawings, and recommendations to the construction team, that might impair or delay the construction process or future design development as part of the later stage of this scope. | 2 weeks |
|  | Part II Renewing and redesigning the urban plan, including: - Addition of secondary roads and land plot access roads - Update of all the necessary drawings for roads, underground and above-ground networks, buildings (if any), signage, facilities, lighting, etc; - Addition and update for all network connection points for land plots - land subdivision and registration drawings; - temporary rain and stormwater drainage system for construction works; - material and item specifications and schedules; - required calculations; - approval with the Client Drawings based on changes made to the design that might impact the construction process or change the direction of ongoing construction works must be provided to the client during the design development phase. | 4 weeks |
| II | Detailed design development and updated Tender* package: Part I Detailed design and construction documents for all roads, networks, buildings and facilities, and accessories, signage, lighting, etc. including: - updated detailed architectural and urban planning drawings - updated GDG submission package - updated cadastral registrations drawings and servitudes as necessary for utilities and roads - construction drawings, plans, sections, elevations, details, etc (scales as necessary to allow detailing and dimensions as comprehensive as possible); - installation drawings and shop drawings; - structural drawings (for foundations, reinforcement walls, etc.) - vertical planning and engineering drawings; - all network and MEP communication plans, and drawings (including installation drawings); - required calculations (incl. traffic analysis, existing network load calculation, MEP calculations, etc.) - bill of quantities; - material and accessory schedules and specifications; - cost estimates; | 6 weeks after the client’s approval of the Concept Design. |
|  | Part II Update Tender* packages for procurement of new construction works for all parts of detailed design and construction projects (which were not part of the existing design package and were added, changed, or updated as part of this scope). Reconcile the new tender package with existing (old) tender documents and create new unified and complete set of drawings, BoQs, cost estimations, calculations and set of all necessary construction drawings and documents. | 1 week after the client’s approval of the Detailed Design. |
| III | Authorial-Technical supervision: To ensure that the construction company complies with provided detailed design and documents. | Commissioned separately by the Client |

* As some stages of the construction process will be already tendered out and ongoing according to the existing design, the new tender documents which are part of this scope will include updates, changes, or new additions, that were made to the existing design project. The new tender package should merge all the information that is unchanged from existing (old) tender package and create updated, unified and complete combined set of documents.

All deliverables should be provided in Georgian and English Languages. All drawings and specifications should be bilingual in Georgian and English.

Deliverables will also include 1 CD with all documents in PDF file format with 300dpi resolution and DWG files including plans, elevations and sections.

BoQs and other chart documents should be provided in Excel file format.

The Consultant must prepare all documents, drawings and design package data according to Georgian and Municipal laws and requirements, considering best international standards and practices.

The Consultant should update submitted documents, drawings and design package according to Client’s comments or requirements from Municipality.

Contact Information

For questions or concerns connected to this RFP, we can be reached at:

Aleksandre Okroshidze
Construction Director

M: +995 595 129 977
E: aleksandre.okroshidze@tbilisihills.com

Vakhtang Makasarashvili
Chief Architect

M: +995 598 62 02 12
E: vakhtang.makasarashvili@tbilisihills.com

Lela Vakhtangishvili
Head of Procurement Department

M: +995 598 299 991
E: lela.vakhtangishvili@tbilisihills.com

Appendix

Appendix #1 – Existing Road and Networks Design Package, and Land Plot Division Drawings

- Topographical survey;

- Geological Survey;

- Existing Road profile;

- Existing masterplan with identification of sold plots and problematic plots;

- Existing utility network design;

- Urban planning regulations for residential land plots according to GDG;

- Numeration of existing land plots.