Program Consortium: World Vision Germany, Danish Refugee Council (DRC) and World Vision Georgia Foundation (WVGF)

Train targeted household members on entrepreneurship as well as small business development and management

Terms of Reference

2025

Contents

Acknowledgments	3

Glossary	3

Introduction and Background	4

Who we are	4

Project Overview	4

Knowledge Hub	6

Gender, Displacement and Poverty	6

Consultancy Purpose	7

Purpose of the Assignment	7

Deliverables and Payment terms	8

Methodology	9

Required Expertise and Qualifications	10

Application package to be submitted by applying organization.	10

Proposal Evaluation and Selection	Error! Bookmark not defined.

# Acknowledgments

The present Terms of Reference, with the aim of delivering the Training for the targeted households’ members in the ERTAD project on entrepreneurship as well as small business development and management have been developed by the Danish Refugee Council (DRC).

The ToR described herein consists of our own work, undertaken to secure funding, implement the activities, describe, and advance learning. All the materials elaborated through the process remains the property of the project partners described in this document and cannot be used for private or third part purposes.

# Glossary

WVGF		World Vision Georgia Foundation

DRC		Danish Refugee Council

GA		Graduation Approach

IDP                      Internally Displaced Person

NEET                  Not in Education, Employment or Training

GoG		Government of Georgia

LEPL 		Legal Entity under Public Law

SIDA                   Swedish International Development Agency

SSA                     Social Service Agency

GBV                    Gender Based Violence

KII                       Key Informant Interview

HH	Household

HEC                    Household Empowerment Consultant

# Introduction and Background

## Who we are

World Vision Georgia Foundation is a relief, development, and advocacy organization that has been working with the most vulnerable children, their families, and communities since 2000. The primary objective of WVGF is to tackle the root causes of vulnerability and injustice and by doing so, help the most vulnerable to live life in fullness. Throughout its 25 years of operation in Georgia, World Vision has been working to strengthen the child welfare system and create a healthy and active society for children that is inclusive, tolerant, and provides equal opportunities for all. In its work towards the overarching mission of the organization, WVGF recognizes a holistic approach whereby the improvement of a child’s well-being is inextricably linked to the overall ability of the child’s family and the community to provide welfare for the child. With active grassroots engagement, WVGF builds local capacity and creates an active civil society in the regions of Georgia to achieve sustainability of its developmental efforts.

DRC (Danish Refugee Council), founded in Denmark in 1956, is Denmark’s largest and the world’s leading non-profit, independent, rights-based refugee organization. Organization’s vision is to assist refugees, internally displaced people, and their host communities to a dignified life. DRC protects lives and human rights and empowers beneficiaries throughout conflict displacement by providing shelter, food, and hope in terms of work, education, and integration towards a sustainable future. Since 1998, programmes in the South Caucasus are designed through a “protection lens”, ensuring that all activities integrate protection principles. As such, organization will continue to work on expanding its knowledge and ensure durable solutions are provided to IDPs, returnees and host communities, and as well as make IDPs, returnees, host communities and persons in a refugee-like situation aware of and actively claim their rights, through legal assistance and awareness raising.

# Project Overview

In line with its strategic aspirations, from January 1st, 2023, WVGF together with the implementing partner DRC in Georgia and pin partnership with LEPL Social Service Agency, has launched the project “Supporting Poverty Alleviation in Georgia through Graduation Approach”, with the financial support of SIDA.

The overall goal of the project is to contribute to reducing poverty and increase the resilience of ultra-poor households in 5 regions in Georgia, namely Kakheti, Imereti, Samtskhe-Javakheti, Adjara and Samegrelo Zemo Svaneti, and the incorporation of Graduation Approach (GA) principles and measures into national and subnational poverty reduction programs/schemes in support of the poverty reduction efforts of the GoG. The project will be implemented in locations with high IDP concentration, as well in urban and rural settings with non-IDPs across a range of vulnerable groups following a Human Rights Based approach. In this regard, the project will have two main directions - Direct Support to the most vulnerable and Capacity Building/Technical Assistance of duty-bearers - building up one Knowledge Hub and integrating the approach already well-tested in other contexts into the Georgian social service system.

The project is implemented in urban and rural areas of the following regions:

- Samegrelo Zemo Svaneti region: Zugdidi, Senaki and Poti municipalities

- Imereti region: Kutaisi, Tskaltubo, Zestaponi and Khoni municipalities

- Kakheti region: Telavi and Kvareli municipalities

- Samtskhe-Javakheti region: Akhaltsikhe and Adigeni municipalities

- Adjara region: Batumi municipality

The project aims to tackle the challenges of the Government of Georgia in its poverty alleviation efforts by introducing a sustainable multifaceted, and holistic approach named Graduation Approach (GA) to propel people onto the path out of poverty, going beyond just financial aid, tackling not only their economy but also their social exclusion, building on participation and inclusion. Graduation Approach is a leading evidence-based approach of DRC and World Vision work worldwide that contributes to organizational commitment to reduce child vulnerability among the poorest communities. By helping to transform households through inclusive and scalable interventions, Graduation empowers families with the most vulnerable ones to equitably shape their future and that of their children. The approach has a strong gender-transformative power due to its focus on gender-transformative interventions.

The Graduation Approach has been refined through rigorous application and evaluation, leading to a set of standards, which promote consistency, effectiveness, and scalability, while allowing it to be adapted to different contexts. Four pillar approach, with accompanying minimum standards, strikes this balance by identifying flexible intervention areas, alongside essential standards to ensure quality and rigor within the programme. These four pillars are: social protection, livelihoods promotion, financial inclusion, and social empowerment. The GA identifies individuals living in extreme poverty and provides them with basic resources, assets to kick start livelihood and/or income-generating activity, financial education, technical training, life-skills coaching, and social support in addition to facilitating their access to social services on multiple levels so that they can “graduate” from the program with sustainable sources of income, be food secure and integrated into community schemes as well as having the sustainable social protection net.

The program as pilot will work under the two major outcomes:

Outcome I will ensure that through the roll-out of the Graduation Approach (GA) Model, ultra-poor households (780) have improved their economic situation, food security and resilience through assistance with essential livelihoods and food consumption items, acquisition of technical skills and capacities in key economic livelihoods areas, building of knowledge and skills in financial planning and management, increased access to social and financial services, the development of positive mindsets/attitudes and the participation in community structures and networks.

Outcome II The project aims to strengthen the capacity and enhance the capability of national and municipal government agencies, and their coordination through the establishment of one GA knowledge Hub acting as a competence dissemination mechanism to reduce poverty more comprehensively, effectively, and sustainably in Georgia. The mechanisms will also ensure effective transfer of GA model, test tools and practices to relevant stakeholders in charge of poverty alleviation, directly or indirectly. The second outcome will therefore firmly embed the GA model into the Georgian duty-bearers’ response framework towards poverty alleviation. It will thereby strengthen their capacity and enhance capability to fulfil their obligation to realize human rights for all, including their capacity to ensure accountability, transparency, participation, and non-discrimination.

## Knowledge Hub

In pursue of Outcome 2, while applying newly imported tools, practices, and systems as pilot under Outcome 1, the project relies on the establishment of one Knowledge Hub as one multi-dimensional and multi-layer integrated platform. The Knowledge Hub stands for the overall structure of coordination to facilitate the provision of Technical Assistance under Outcome 2.

The Knowledge Hub primarily consists of one Knowledge Hub Management Unit and further declines into other sub-platforms of coordination such as the Core Reference Group (CRG) and Sub-Reference Groups (SRGs) as outlined below, as for their responsibilities and duties.

## Gender, Displacement and Poverty

Unequal gender dynamics significantly impact women's participation in entrepreneurship, limiting their access to resources, financial services, and decision-making opportunities. Women entrepreneurs face systemic barriers, including discriminatory social norms, limited access to education and professional networks, and a lack of collateral needed for business loans. They are also burdened with unpaid domestic tasks and caregiving responsibilities due to the absence of widely available childcare services, restricting their time and mobility to engage in entrepreneurial activities. In rural and agricultural sectors, women are often excluded from decision-making processes and lack access to advanced technologies and machinery, which are perceived as men’s domain. They are typically engaged in manual labor with limited opportunities to enhance productivity or scale their businesses. This reinforces traditional gender roles and limits their economic empowerment. Additionally, women in entrepreneurship are frequently concentrated in low-profit sectors, facing challenges in accessing high-growth industries due to gender stereotypes and market segmentation.

Poverty significantly affects entrepreneurial potential by restricting access to financial resources, education, and social networks. Women living in poverty face compounded challenges due to gender-specific constraints, including unpaid domestic labor, lack of childcare support, and discriminatory norms that limit their economic participation. As a result, they are often confined to informal, low-profit ventures with minimal growth prospects.

Entrepreneurial opportunities for women in low-income communities are typically limited to traditional sectors with high competition and low-profit margins, such as food processing, handicrafts, and small-scale retail. These sectors are vulnerable to economic shocks and lack scalability, perpetuating the cycle of poverty.

Financial exclusion is another critical barrier, as women in poverty frequently lack collateral, credit history, and financial literacy to access formal banking services. This exclusion restricts their ability to invest in business growth, technology adoption, and market expansion.

# Consultancy Purpose

The primary objective of Entrepreneurship Training for Target Households – in the scopes of the project is planned to deliver entrepreneurship training to target household members. These training sessions aim to equip beneficiaries with basic knowledge and skills in entrepreneurship.

Training on Entrepreneurship - Entrepreneurship module and manual have been developed in the scopes of the project. These resources comprehensively address essential topics for entrepreneurial activities. The module and the respective toolkit were contextualized and applied to train selected Master Trainers in relevant fields. DRC enhance entrepreneurial capacity and gauge willingness to start businesses of beneficiaries proving to have highest potentials.

## Purpose of the Assignment

This technical assignment focuses delivering the simplified three-day training course based on the existing Entrepreneurship manual.

The Specific Objectives of the consultancy focus on conducting entrepreneurship trainings for household members and providing post-training consultations:

- To ensure that the training materials and practical examples of the trainings are directly based on the target households’ existing business ideas. The consultancy will tailor the content to reflect the specific needs and realities of the target households, enhancing the relevance and applicability of the training.

- To enhance the target Household members’ entrepreneurial and business skills and competencies: The training will provide knowledge and strengthen the target households’ capacity in marketing, business management, accounting, business registration, budgeting, financial planning and other related issues, relevant to the small-scale business initiatives.

- To ensure high-quality Business Plan and financial document submission – Following the training, the consultant will provide structured post-training consultations for the Household Empowerment Consultants, based on the collected Business Plans of the households to support them in refining existing Business Plans and financial documents, ensuring high-quality submissions.

Target Audience

The training participants are the ERTAD project household members, from Samagerelo: Zugdidi, Senaki, Poti; Imereti: Kutaisi, Khoni, Tsklatubo, who are supposed to further be supported through the small scale grants and start their entrepreneurial activity in the scopes of the project.

The training module and sessions has to be tailored to their existing business ideas and aiming to be reshaped and refined afterwards.   These beneficiaries typically possess minimal or basic knowledge and skills in entrepreneurship and business management.

# Deliverables and Payment terms

Conducted simplified face to face training on Entrepreneurship in Zugdidi municipality (three-day format, or can be negotiated based on the consultants’ proposed methodology) tailored for target household members conducted for up to 40 participants, in two groups (one in Imereti region and one in Samegrelo).

Conducted consultations (at least 2 full day face to face and 4 full day online consultations)  for the Household Empowerment Consultants based on the collected Business plans of the target households providing recommendations for improvement.

Training Content

The training course should cover, but is not limited to the following:

- Basics of entrepreneurship and business management;

- Practical steps to start and manage a small business;

- Business registration and taxation;

- Financial Planning and Budgeting.

By addressing these objectives, the training will support the project's overarching goal of empowering target families to improve their livelihoods through entrepreneurship.

The consultancy deliverables will be structured into two key phases, with the payments made in two instalments based on the completion of each phase:

|  | Activity | Deliverable | Payment | Timeframe |
| --- | --- | --- | --- | --- |
| 1 | Entrepreneurship Trainings - Conduct entrepreneurship training sessions for household members, ensuring that materials and practical examples are based on their existing business ideas. - Adapt and enhance training materials to align with the specific needs of the target households. - Equip participants with the necessary knowledge and skills to develop their Business Plans and financial documents. | Completion of training sessions and submission of a training report, including participant feedback and key learnings. | The first instalment of the consultancy fee will be reimbursed upon successful completion of the training sessions and submission of the training report. | 2 weeks (April 2025) |
| 2 | Post-Training Consultations - Provide individual and/or group consultations to household members to refine and finalize their Business Plans and financial documents. - Ensure that Business Plans and financial documents meet the required quality standards before submission to the Regional Mentor and Household Empowerment Consultants. - Offer guidance on practical implementation and sustainability of business ideas. | Completion of post-training consultations and submission of a final report summarizing the outcomes, progress of participants, and recommendations. | The remaining instalment of the consultancy fee will be reimbursed upon successful completion of the post-training consultations and submission of the final report. | 3 weeks (May 2025) |

# Methodology

Based on the context and the interests of the target groups, as described above, the additional training course should be basic and simple (easy to understand and relevant to the micro and small business initiatives) and include information based on the developed manual on the following issues:

Business administration and management

- Starting and managing business (the business cycle from start to income generation)

- Setting business goals and forming an idea

- Identifying and allocating resources

- Analyzing competitors

- Market structure

- The role of marketing/social media and communicating with customers

- Identifying business risks and ways to respond

- Producing and managing necessary documents, including contracts

- The importance of a business plan and developing the business plan

Entrepreneurship

- Forms of entrepreneurial activity and Georgian tax legislation;

- Existing taxes and special types/benefits/advantages (focused on small, micro and individual entrepreneurs);

- Record keeping and financial documentation of the entrepreneurial activities (invoices, purchase orders, acceptance acts, etc.)

Financial planning and Budgeting

- Financial planning

- Profit and Loss Statement

- Cost Calculation

- Cash Flow Projection

- Budgeting

Training should include practical exercises and share best practices.

# Required Expertise and Qualifications

An consultancy company with the following expertise and qualifications:

- Demonstrated experience in delivering training sessions in entrepreneurship, business development.

- Ability to tailor training materials and methodologies to reflect the existing business ideas and needs of the target households.

- Strong facilitation and coaching skills, with the capacity to provide post-training consultations to ensure high-quality Business Plan and financial document preparation.

- Experience working with diverse communities, particularly in household empowerment or livelihood development programs, is an asset.

## Application package to be submitted by applying organization.

- Company track record of relevant services.

- CVs of trainer(s)/consultant(s);

- List of trainings conducted within the last 3 years with the mentioned target audience and training topics.

- Recommendation letters (at least one letter) from previous donor/contractor

- Technical proposal with detailed timeline, and estimated budget (with a detailed breakdown of costs per unit, indicating consultants daily rate). Be noted, to consider the Deliverables and Payment terms and base the budget proposal on the relevant two phases.

- Budget should be presented without VAT.

The abovementioned documents should be sent in PDF format to: rfq.geo.tbs@drc.ngo, no later than March 17th 2025 17:00 pm, Please indicate the following assignment title in the subject line of the email “Train targeted household members on entrepreneurship as well as small business development and management”, otherwise your application will not be considered.

Approval:  Mariam Nanitashvili

Requester: Mzevinar Jojua

Manager : Ketevan Patsatsia

Finance : Sandro Tchitchinadze

Date : 04.03.2025