Annex 1

Terms of Reference

Information Campaign to Raise Awareness in Georgian Society on:

- Trafficking in Street Children

- Recruitment for labour emigration and labour immigration

- Introduction

The Mission to Georgia of the International Organization for Migration (IOM), United Nations Migration Agency, invites interested parties to submit proposals to partner with IOM for the design and production of two specific information campaigns.

These terms of reference provide the details of the products to be delivered to IOM and is an official attachment to the Request for Quotation (RFQ) released by IOM.

- Background

In 2025, IOM has scheduled a comprehensive information campaign across the territory of Georgia to inform relevant target groups about topical issues related to 1) recruitment for labour immigration and labour emigration and 2) trafficking in children for street begging and preventive action.

This information campaign will consist of two separate lots, namely:

LOT 1:	One nation-wide, multi-media information campaign on labour migration concerning the revised regulations in place concerning a) recruitment by the private sector of employees in Georgia for employment abroad, and b) employment of foreign nationals in Georgia by Georgia-based employers.

LOT 2:	One specifically tailored campaign focusing on child begging and awareness-raising of Georgian society about measures that can be taken to discourage this form of trafficking in human beings, focusing in particular on Georgia’s three largest urban agglomerations (Tbilisi, Batumi and Kutaisi).

This combined action is part of the following project that IOM is implementing in Georgia, namely:

- “Improved Specialization in Migration Governance and Integrated Border Management in Georgia (SPECS, IOM reference: IB0407)”, funded by the Delegation of the European Union to Georgia.

- Overall objective of the information campaigns

To increase awareness and knowledge levels of the relevant target groups of the two information campaigns about the principal aspects of both labour migration and child begging and to empower the target groups to use that knowledge for the protection of the rights of themselves and third persons.

- Purposes of each specific information campaign

LOT 1

Thanks to the multi-media campaign on labour migration, society at large and specific target groups have:

- Increased their levels of awareness and understanding about the basic concepts and regulations of employment overseas as well as employment of foreigners in Georgia.

- Increased the understanding how Georgia-based employers shall apply the revised procedures for recruiting foreign work force and how to register employment contracts for the purpose of certification and monitoring by relevant state bodies.

- Appreciated how to take preventive action to ensure that prospective labour migrants do not fall prey to unscrupulous employers.

LOT 2

Thanks to the multi-media campaign on child trafficking, society at large and specific target groups have:

- Raised awareness about the criminal behaviour of those persons, who are behind child begging schemes on the street.

- Understood that no single child will agree to be forced to beg on the street. Therefore, each and every child begging on the street is a priori a victim of human trafficking.

- Received the message that giving money to exploited children will not help these children, but rather enrich the people who are responsible for exploiting those children and, thus, sustain the crime rather than alleviating the fate of children.

- Indicators to measure successful implementation of the information campaigns

- Numbers of locations at which campaign material is displayed/disseminated.

- Number of outreach and awareness raising events organized or supported.

- Number of participants in awareness raising and outreach events/initiatives.

- Number of views/likes/shares of relevant campaign material on social media.

- Required Deliverables and Implementation Modalities

LOT 1:	Campaign on labour migration

While the Government of Georgia has engaged with counterparts in the EU in discussions and negotiations on legal labour migration pathways to the EU for citizens of Georgia, no consolidated efforts have yet been undertaken to inform the population of Georgia about the results of those efforts. At the same time, over the past decade Georgia has gained also the position of an attractive country of destination for migrant workers from third countries, who are looking for work opportunities in Georgia.

For those circumstances and in light of the changes effected in 2023 to the Law “On Labour Migration”, the Ministry responsible for managing labour migration (the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs – MoLHSA) has developed an informative web portal available on https://labourmigration.moh.gov.ge/.

The following groups of people will be targeted by the information campaign:

- Prospective labour migrants (citizens of Georgia who are interested to work abroad).

- Private recruitment agencies that recruit workers for employment abroad as well as in Georgia.

- Employers in Georgia who are interested in hiring foreign workers.

- Foreigners who are interested in finding employment in Georgia.

The multi-media information campaign will convey clear messages about labour migration regulations in Georgia, the possibilities for temporary legal employment abroad, rights and benefits of citizens of Georgia, existing regulations in the receiving country as well as the risks of irregular (labour) migration.

Campaign material will have to be produced in two languages, namely Georgian and English.

Preferred Tools and Approaches:

- Multimedia Approach:

Utilize a diverse range of multimedia tools to create engaging and impactful campaign materials. This includes producing high-quality videos, designing informative infographics, creating eye-catching posters, and leveraging digital media for broader engagement. The goal is to develop content that is visually appealing, informative and shareable across various platforms.

  - Production of 3 Videos: 1. Graphic Video on Legal vs. Illegal Migration: highlighting the risks associated with illegal immigration and the use of illegal facilitators, while also presenting the benefits of legal pathways and the current regulations in place for employment recruitment agencies. 2. Human Story of a Georgian Migrant: using legal pathways to work abroad, sharing personal experience and demonstrating the benefits and ways of safe, humane, and orderly migration. 3. Human Story of Foreign Labour Migrants in Georgia: portrays the experiences of foreign labour migrants working legally in Georgia, highlighting their journey and showcasing the positive impact of legal migration on both the migrants and the host country.

  - Infographics/Posters: Design infographics and/or posters that present complex information in a clear and visually appealing manner to illustrate statistics, explain processes, and highlight key points of the campaign. Materials that can be used for both online and offline promotion, visually striking and include key messages and calls to action. They can be displayed in public spaces, shared on social media, and used in digital advertising campaigns.

- Outdoor and Social Media Ads:

  - Implement outdoor advertising through banners and posters for the duration of one month. Display at least 2 outdoor banners in various means of transportation and at busy transportation hubs and other venues where many people congregate (such as, for example, underground stations, bus stops, Public Service Halls, airports etc.).

  - Social media ads should run for a duration of one month on the following platforms: Facebook, LinkedIn, YouTube, and Instagram. The campaign's success will be measured using metrics such as reach, impressions, engagement, and click-through rates. The ads should achieve a minimum reach rate of 50,000 users per platform. The vendor is responsible for ad creation, placement, monitoring and optimization, ensuring compliance with platform-specific policies and brand guidelines. Regular performance reports should be provided to track progress and make necessary adjustments.

- Collaboration with a Podcaster:

  - Engage a podcaster with a significant following, whose topics align with the campaign's subject matter. If a suitable local podcaster is not available, the vendor can produce their own podcast featuring key speakers such as representatives from IOM, recruitment agencies as well as labour migrants. These speakers will discuss the new regulations governing overseas employment and the employment of foreigners in Georgia. The podcast should be informative and engaging, providing valuable insights into legal migration pathways. The content can then be repurposed into short reels and promoted on digital platforms like YouTube and other social media channels to maximize reach and impact.

The desired duration of the information campaign will be 6 weeks.

LOT 2:	Campaign on street begging of children

IOM is keen to develop and implement an information campaign on children that are forced to beg on the streets of Georgia. The campaign will carry a particular focus on raising awareness of society about: a) the criminal behaviour of the persons, who are behind child begging schemes and b) that giving money to exploited children will not help them, but rather sustain the crime and enrich the people responsible for exploiting those children.

The campaign on street begging of children will be implemented with specific emphasis on Georgia’s three biggest urban agglomerations, namely Tbilisi, Batumi and Kutaisi.

This campaign shall consist of the following components:

Preferred Tools and Approaches:

- Multimedia Approach:

  - Utilize a diverse range of multimedia tools to create engaging and impactful campaign materials. This includes producing an image video, creating eye-catching posters, and leveraging digital media for broader engagement. The goal is to develop content that is visually appealing, informative and shareable across various platforms.

  - Audio-visual ads will be produced for display on national and local TV stations and on relevant social media platforms.

- Outdoor and Social Media Ads:

  - Implement outdoor advertising through banners and posters for the duration of one month in three biggest urban agglomerations, namely Tbilisi, Batumi and Kutaisi.

  - Display at least 2 outdoor banners in various means of transportation and at busy transportation hubs and other venues where many people congregate (such as, for example, underground stations, bus stops, Public Service Halls, airports etc.).

  - Social media ads should run for a duration of one month on the following platforms: Facebook, LinkedIn, YouTube and Instagram. The campaign's success will be measured using metrics such as reach, impressions, engagement and click-through rates. The ads should achieve a minimum reach rate of 50,000 users per platform. The vendor is responsible for ad creation, placement, monitoring and optimization, ensuring compliance with platform-specific policies and brand guidelines. Regular performance reports should be provided to track progress and make necessary adjustments.

- Creative Collaboration with an Artist/Painter:

  - Engage a renowned and experienced artist or painter to develop a painting or a series of paintings that depict the issue of street begging among children. This artwork can be created both graphically and physically, providing versatile options for use during the campaign. Given the sensitivity of the subject, it is advisable to avoid using real photos of children engaged in street begging. Instead, a more creative and illustrative approach would be desirable. The artist's work should evoke empathy and raise awareness about the issue without compromising the dignity of the children. The selected artist should have a significant following and a strong presence in their field, which can be leveraged to disseminate the campaign message more effectively. Additionally, the illustrations created can be used to produce various merchandise or visibility materials, further extending the reach and impact of the campaign.

or

- Creative Collaboration with a Film Director:

  - Collaborate with a skilled film director to produce a short film, no longer than 5 minutes, that portrays the poignant story of street begging among children. The film can be either animated or graphical, depending on the director's expertise and the campaign's needs. The scenario should address common misconceptions about street begging and be crafted to touch the audience's emotions, creating a sentimental and impactful narrative that raises awareness and fosters a deeper understanding of the issue. The film should resonate with viewers, encouraging them to reflect on the plight of children involved in street begging and inspiring them to support the campaign's objectives.

These approaches aim to use creative and impactful methods to raise awareness about the issue of street begging among children, ensuring that the campaign message is both respectful and compelling.

The material to be produced will contain hotline numbers of relevant actors, which may be those state bodies that operate specialized trafficking hotlines (to be confirmed by the donor) and/or hotlines or dedicated social media groups operated by civil society organizations and IOM.

This campaign will carry various messages, inter alia a call on the population and foreign visitors to cooperate with the Georgian authorities and civil society organizations in reporting instances of TIP and for possible victims to offer low-threshold and confidential identification and referral services.

The main slogan of the campaign on child begging can be one or more of the following versions. Interested applicants submitting a proposal under this RFQ can obviously propose any other slogan as they deem fit – the below examples are merely for illustrative purposes:

“Don’t Give Money to Children Begging on the Street – Your Petty Cash Only Sustains the Traffickers!”

“Any Child Begging on the Street is a Victim of Human Trafficking – Call our Hotlines to Report this Crime”

“Exploiting Children in Begging is a Crime… Fighting it is a Duty.”

As concerns the campaign’s concept, all messages and visuals will be presented in a gender-balanced manner, avoiding stigmatization, stressing positive communication approaches rather than portraying trafficking in human beings in a fear-instilling way, but relaying at the same time that trafficking in human beings affects everybody and combating this crime is a collective responsibility.

Campaign material will have to be produced in two languages, namely Georgian and English.

The duration of the information campaign shall be 6 weeks.

- Scope of work

IOM is looking to partner with a socially responsible, creative entity that has experience in storytelling, advocacy and implementation of a national (with focus on Tbilisi, Kutaisi, Batumi), multi-media awareness-raising campaigns, using data, communication and technology as well as behavioral science.

IOM invites interested parties to apply with a letter of interest, outlining the vendor’s understanding of the assignment, their relevant experience, and their proposed approach to fulfilling the project requirements.

The vendor should apply for LOT 1 and LOT 2 together. The proposal should also include a brief overview of the vendor’s qualifications, key personnel, and any initial strategies they plan to implement.

For further details please refer to the Request for Quotation (RFQ), of which this document is an official annex.