Danish Refugee Council (DRC)

“The master classes to provide mentoring and consulting meetings with the winning team of the Social Entrepreneurship Competition in Kaspi Municipality”

For the project:

“Social Entrepreneurship and Enhanced Development-Based Skills-SEEDS- in Georgia and Ukraine” funded by the European Union

Terms of Reference

2025

Contents

Introduction	3

Project Overview	3

General Information	3

Project Summary	3

1.	Master Class purpose and objectives	4

Required Expertise and Qualifications	5

Application package to be submitted by applying by registered Companies/Individual Entrepreneurs.	5

# Introduction

DRC (Danish Refugee Council), founded in Denmark in 1956, is Denmark’s largest and the world’s leading non-profit, independent, rights-based refugee organization. Organization’s vision is to assist refugees, internally displaced people, and their host communities to a dignified life. DRC protects lives and human rights and empowers beneficiaries throughout conflict displacement by providing shelter, food, and hope in terms of work, education, and integration towards a sustainable future. Since 1998, programmes in the South Caucasus are designed through a “protection lens”, ensuring that all activities integrate protection principles. As such, organization will continue to work on expanding its knowledge and ensure durable solutions are provided to IDPs, returnees and host communities, and as well as make IDPs, returnees, host communities and persons in a refugee-like situation aware of and actively claim their rights, through legal assistance and awareness raising.

# Project Overview

## General Information

Project title: Social Entrepreneurship and Enhanced Development-based Skills-SEEDS - in Georgia and Ukraine

Donor: European Union

Implementing Agencies: DRC Georgia, Youth Innovations Center (YIC), Georgia’s Innovation and Technology Agency (GITA), Tallinn University, Association ATINATI, Mariupol Youth Union (MYU).

Locations: Georgia and Ukraine

Duration:  18 months

## Project Summary

Overall objective: Placing Social Entrepreneurship at the core of an integrated State - CSO response framework to systemically promote the inclusion of disadvantaged youth and contribute poverty reduction in Georgia and Ukraine following a Go Green and Go Digital agenda.

The project builds upon the collected evidence, experience and lessons learnt from the first phase of EU4Youth action during which DRC in Georgia and Ukraine as of December 2018 till September 2021, in partnership with the Mariupol Youth Union in Eastern Ukraine and one partner in Imereti region in Georgia tested innovative dual skills development schemes for vulnerable youth NEETs (Not in Education, Employment or Training). The project also establishes a strong connection with the expected roll out in Georgia as of January 2023 of the World Bank-UNHCR founded initiative Ultra-Poor Graduation (UPG) approach which accompanies most vulnerable segments of the population in their trajectory out of poverty through long-term multifaceted interventions in an integrated manner.

The project will pay a specific attention to reduce structural gaps by engaging strategically on the path of social entrepreneurship mainly through the establishment of innovative incubators in partnership with the Youth Innovations Centre (YIC), the Georgian State Legal Entity under Public Law GITA (Georgia’s Innovation and Technology Agency) and the local NGO Atinati in Georgia, the Tallin University in Estonia with its instrumental link with the local development program NULA Incubator and finally the Mariupol Youth Union (MYU) in Ukraine for scaling up purposes.

The project works under the two major outcome:

Outcome 1: To create an institutionalized competence framework at state level in Georgia to position with participation of CSOs Social Entrepreneurship at the centre of youth inclusion and career management policy in Georgia in anticipation of a viable replication to Ukraine in support of its recovery efforts.

Outcome 2: To pilot in Georgia based on one newly defined competence framework an innovative social entrepreneurship incubator model and career management paradigm in the green and digital economy as a foundation for the adoption of more integrated youth entrepreneurship trajectories in Georgia and Ukraine

BioNova is the innovation Social Enterprise start up that has been established by the incubator participants of the project, upskilled youth leaders in Georgia, Kaspi Municipality. BioNova converts organic waste into biogas, electricity, and biofertilizer using compact, user-friendly devices tailored for small scale farmers. By solving waste management challenges, BioNova helps farmers reduce costs, improve soil health, and achieve energy independence, which significantly reduces gas emissions. Their solutions empower farmers to increase productivity and contribute to environmental protection.

- Master Class purpose and objectives

The master class aims to provide mentoring and consulting meetings with the winning team of the Social Entrepreneurship Competition in Kaspi – BioNova,  Specifically:

The objective of the masterclasses is to provide BioNova’s team with targeted mentoring and expert-led sessions that support the refinement of their existing prototype—ensuring its alignment with industrial standards, technical safety requirements, operational efficiency, and adaptability to the realities of local farming practices.

The specific objectives are:

Organize and ensure delivery of the masterclasses led by international experts to provide specialized guidance and mentoring to the BioNova team.

Ensure the procurement and delivery of the necessary equipment required for the development and improvement of the prototype, in alignment with the technical recommendations provided during the masterclasses.

The masterclasses aim to achieve the following objectives:

- Conduct a comprehensive review and technical assessment of the existing system to identify strengths, weaknesses, and areas for improvement.

- Refine the design and provide detailed technical specifications to ensure the prototype meets industrial standards and local needs.

- Identify the necessary equipment and develop an effective procurement strategy aligned with the project's goals and budget.

- Develop a step-by-step assembly guide and conduct a risk assessment to address potential technical challenges during implementation.

- Support the planning of implementation and define next steps for further development and scaling of the prototype.

The masterclasses will be delivered by international experts over a minimum of five days and can be conducted either online or in person, depending on feasibility and availability.

In addition to the masterclasses, the contractor is expected to procure and deliver the equipment necessary for the prototype, as specified by the BioNova team. See List of Masterclasses and   Necessary items

| Key Deliverables: |  |
| --- | --- |
| Deliverable 1 | Team Introduction and Prototype Review Report - Meet and introduce the team, review their prototype, and conduct a thorough assessment of their needs (especially the required items) - Refine and adjust the masterclass plan accordingly, ensuring alignment with their objectives and requirements - Develop a detailed action plan outlining the next steps and timelines and define the actual list of items to be purchased - Identify relevant experts to support the team and begin collaboration with the selected experts. |
| Deliverable 2 | Procurement of Necessary Equipment and Acceptance Act Between the Bionova and the Consultant - Procure the necessary Equipment (Annex 2) and materials required for the successful execution of the masterclasses and prototype work. - Ensure that all necessary items are obtained in line with technical specifications. |
| Deliverable 3 | Masterclass Implementation report - Conduct the masterclasses, ensuring that the content is tailored to the team's needs, incorporating expert insights and practical demonstrations. - Provide ongoing support and guidance throughout the duration of the masterclasses. |

## Estimated Timeframes for Deliverables:

Team Introduction and Prototype Review - Timeline: April 29th  - May 3rd;

Procurement of Necessary Equipment - Timeline: May 4th  - May 10th ;

Masterclass Implementation - Timeline: May 11th - May 19th.

## Required Expertise and Qualifications

The consultant with the following expertise and qualifications:

- Relevant Academic Background: Advanced university degree in a field related to science, technology, engineering, or a relevant discipline.

- Experience in Program or Event Development: At least 5 years of hands-on experience in conceptualizing, designing, and delivering educational events, masterclasses, or interactive science shows, preferably for diverse audiences.

- Strong Communication Skills: Demonstrated ability to present complex technical concepts in an engaging and accessible manner.

## Application package to be submitted by the applying organisation/Individual Entrepreneurs.

- List of similar masterclasses, consultations or mentorship conducted within the last 5 years with a similar audience and training topics.

- CVs of the Key personnel;

- Technical proposal with detailed timeline, and estimated budget (with a detailed breakdown of costs per unit, indicating consultants daily rate).

- Budget should be presented without VAT.

The abovementioned documents should be sent in PDF format to: rfq.geo.tbs@drc.ngo, no later than April 24th, 2025  18:00 pm. Please indicate the following assignment title in the subject line of the email “The master classes to provide mentoring and consulting meetings with the winning team of the Social Entrepreneurship Competition in Kaspi Municipality”, otherwise, your application will not be considered.

Proposal Evaluation and Selection

The evaluation is made on a technical and financial basis. The proposed technical offers by bidders will be evaluated using the following criteria, and points will be allocated on a scale from 1 – 10 for each of the criteria stipulated below, whereas the weighting is as follows:

| Proposed services (100%) | - Content of the proposal is suitable for and meeting DRC’s requirements (50%) - Demonstrated understanding of the ToR (20%) - Realistic implementation strategy (30%) |
| --- | --- |
| Total | 100% |

All bidders must obtain an average score of at least five for the total technical scoring in order to proceed to the financial evaluation. The financial offer will then be weighed against the technical offer.

The final decision will be made after the interview (if applicable – the consultant is a physical person), considering applicants’ relevant experience, qualification, and cost efficiency of the offer.

Tentative list of Masterclasses

Day 1: System Review and Technical Assessment

Objective: Review the existing design and define the technical requirements for the MVP.

- Presentation of BioNova’s current design and concept

- Engineer's assessment of the digester type, size, and energy production goals

- Analysis of organic waste inputs (fecal matter, food waste) and expected biogas yield

- Identification of weaknesses and opportunities for improvement

Outcome: Technical review report and updated MVP goals

Day 2: Design Refinement and System Detailing

Objective: Finalize the technical configuration based on the engineer's recommendations

- Discussion of materials, insulation, and pressure control

- Input/output mechanisms for waste and biogas storage options

- Selection of sensors and control elements, if needed

- Preparation of detailed diagrams and notes for MVP construction

Outcome: Refined technical design with diagrams

Day 3: Equipment Identification and Procurement Strategy

Objective: Finalize the list of required materials and components

- Engineer to break down the system into key components: tanks, valves, gas holders, mixers, etc.

- Recommendations on specifications, suppliers, and pricing

- Discussion of local vs. imported alternatives

Outcome: Detailed Bill of Materials (BoM) with pricing and supplier options

Day 4: Assembly Guide and Technical Risk Assessment

Objective: Prepare for system construction and operation, with safety in focus

- Step-by-step assembly instructions, required tools and materials

- Identification of potential risks and preventive measures

- Maintenance schedule and system lifecycle planning

Outcome: Assembly manual and safety protocol documentation

Day 5: Implementation Planning and Next Steps

Objective: Develop a detailed plan for MVP testing and future scaling

- Planning the first test: what to measure, how to define success

- Engineering guidance based on environmental specifics

- Monitoring systems (mechanical or digital) tailored to local conditions

- Final Q&A session and recommendations for future technical development

Outcome: Testing plan and roadmap for further improvement

Final Result:

Following this 5-day collaboration, BioNova will have a technically validated and refined MVP design, a complete and itemized list of required materials, a safe and structured assembly plan, and a clear roadmap toward testing and full implementation. The involvement of an expert engineer will enhance the project’s technical credibility and increase the likelihood of successful outcomes.

## Necessary items

| # | List of Item | Characteristic | Number of Items |
| --- | --- | --- | --- |
| 1 | Biogas compressor | Operating power: 20 W Voltage: 220 V Maximum gas pressure: 18 kPa Maximum gas flow rate: 1.2 m³/hour Maximum transmission distance: 300 meters Package weight: 1.5 kg | 1 |
| 2 | Biogas Dehydration Purification Pipe Hose Appliance Equipment | Dimensions: 150 × 100 × 65 mm Gas source: Biogas Material: PVC Capacity: 0.5 liters | 5 |
| 3 | Biogas Filter Iron Oxide Desulfurizer | Density: 0.85 kg/L Corrosivity (k): 50–60% Tank material: Iron-plastic composite Biogas processing capacity: Less than 50 m³ per day Regeneration: Twice H₂S removal efficiency: Over 99% | 5 |
| 4 | 16 KPA pressure gauge | Outer diameter: 10 mm Maximum pressure: 16 kilopascals (kPa) | 5 |
| 5 | Yellow Iron Oxide for Biogas Pellets | Material: Fe₂O₃ Gas source: Biogas Bulk density: 0.7–0.8 kg/L Air voids: ≥0.3 ml/g Air velocity: ≤500 h⁻¹ Porosity: ≥40% Gas source: Biogas Bulk density: 0.7–0.8 kg/L Air voids: ≥0.3 ml/g Air velocity: ≤500 h⁻¹ Porosity: ≥40% | 5 |
| 6 | 3/4" Compressed Air In Line Moisture / Water Filter Trap | Brand new 3/4" compressed air moisture filter separator with wall-mount bracket. This is a 5-micron filter with a 2.7 oz cup. It is a high-quality filter with a metal bowl and an easy twist-style drain. The filter removes water droplets and debris from your compressed air line to protect and extend the life of your air tools. Specifications: Maximum pressure: 250 PSI | 1 |
| 7 | Heavy Duty Coated Pattern PE Woven Geotextile Hay Tarp | PE woven geotextile hay tarp | 5 |
| 8 | Welding Seamless Stainless Steel Pipe Coil Tube (50 kg) | 201, 304, 316, 316L, 310S, 904L, 2205, 2507 welded stainless steel pipe, coil tube, coiled heat exchanger tube for electric power applications. | 1 |
| 9 | Galvanized steel water tank (10 cubic meters capacity) | PVC tarpaulin tank, bolted galvanized steel water tank, corrugated steel water tank. | 1 |

# ANNEX F

# Transfer of Ownership of Assets

Grant contract identification number: ENI/2021/423-431-01-0008

Title of the action: Social Entrepreneurship and Enhanced Development-based Skills - SEEDS- in Georgia and Ukraine

Name of beneficiary: Danish Refugee Council

Name of local beneficiary/local affiliated entity/final beneficiary of the action to whom the assets are transferred: Social Enterprise “Bionova”

| Assets | Description of item (> EUR 5 000) | Date of purchase | Purchase cost in EUR | Date of transfer / comments |
| --- | --- | --- | --- | --- |
| - Biogas compressor |  |  |  |  |
| - 5 dehydration purification pipes or Biogas |  |  |  |  |
| - 5 Iron Oxide H₂S Desulfurization Filters for Biogas |  |  |  |  |
| - 5 pressure gauges (16 kPa) |  |  |  |  |
| - Iron oxide (20) |  |  |  |  |
| - 3/4" compressed air moisture/humidity filter |  |  |  |  |
| - 5 Waterproof Tent Fabrics – PE Tarpaulin |  |  |  |  |
| - Galvanized Steel Water Tank – 10 m³ Capacity |  |  |  |  |
| - Masterclass |  |  |  |  |
| - Designer services |  |  |  |  |
| - 10 Branded T-shirts |  |  |  |  |
| - 10000 Stickers |  |  |  |  |
| - 56 Hoodies |  |  |  |  |
| - Laser cutter |  |  |  |  |

The above list was drawn up to comply with Articles 2 and 7.5 of the general conditions applicable to EU-financed grant contracts for external action. Ownership of each item listed has been transferred. The local beneficiary(ies) and/or the local affiliated Entity(ies) and/or final beneficiaries are in agreement with its content.

Done in : 		on

_______________			________________________________		________________________________

(Beneficiary)			(local beneficiary/local affiliated entity/final beneficiary of the action No 1)	
				(local beneficiary/local affiliated entity/final beneficiary of the action No 2 	etc.)

Name & Position			Name & Position									Name & Position

English translation can be not accurate and has to be agreed with the consultant at the initial meeting by the team

Specifications will be agreed at the initial stage with the consultant