## ANNEX 1: TERMS OF REFERENCE

EVALUATION OF THE STATE REINTEGRATION PROGRAMME

“ENHANCED OPPORTUNITIES FOR RETURNING MIGRANTS IN GEORGIA”

(Funded by the Swiss Agency for Development and Cooperation (SDC), Reference No.: GE10P0549)

Commissioned by: 	IOM Country Office in Georgia

Evaluation Manager: 	Genci Pjetri

## Evaluation context

The project “Enhanced Opportunities for the Returning Migrants in Georgia”, funded by the Swiss Agency for Development and Cooperation (SDC), implemented by International Organization for Migration (IOM) mission to Georgia in 2024-2028, aims to support the sustainable reintegration of returned migrants in Georgia and improve their economic and social well-being, by enhancing the responsiveness and coordination of national and local stakeholders, improving the contribution of local self-governments and other local stakeholders, including through provision of information and services to returnees, and increasing the opportunities for economic reintegration, social inclusion, and financial inclusion of returnees and their families.

The project adopts a comprehensive approach to migrant reintegration at the individual, community and structural levels, emphasizing a gender-sensitive and human rights-based approach. It builds on existing policies, such as Georgia’s Migration Strategy 2021-2030, while it aims to address gaps in governance, coordination and capacity at both local and central levels.

Recent migration trends in Georgia reveal an increase in returns, especially from EU+ countries, including rejected asylum seekers and long-term migrants, which is straining the reintegration system. Returnees often face difficulties reintegrating due to limited employment opportunities, skill mismatches, psychological distress and restricted access to services. Reintegration efforts are hampered by insufficient support, lack of coordination between central and local authorities and limited involvement of local stakeholders, private sector actors and diaspora networks. While there are several programmes working on reintegration of returnees, economic reintegration remains a significant challenge, coupled with gender-specific barriers impacting female returnees’ economic inclusion.

The main challenge the project intends to tackle is the insufficient and unsustainable reintegration of returned migrants in Georgia, which hampers their social and economic inclusion and limits their potential contribution to the development of their communities and the country.

The overall goal of the project is to enable migrants to achieve economic self-sufficiency, social stability and psychosocial well-being, thereby strengthening their ability to contribute to Georgia’s development. This goal is tackled through the following key objectives:

- Strengthen the institutional capacity of national stakeholders to implement a consolidated comprehensive reintegration framework.

- Empower local self-governance and other local stakeholders to address community development and reintegration challenges.

- Support returned migrants in overcoming employability and employment barriers, improving financial literacy and accessing tailored social services.

- Leverage the diaspora’s expertise and investments to contribute to the local economic development.

The Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs (MoLHSA) is the lead partner of the project, responsible, inter alia, for the implementation and for coordinating the revision of the State Reintegration Programme and the reintegration framework. The priority interest of MoLHSA in this regard is to improve the effectiveness and efficiency of the reintegration support to returnees, enhance coordination and cooperation with other stakeholders, and further align the reintegration framework with the national policies and strategies.

The present evaluation is intended to assess the current State Reintegration Programme (SRP) and provide recommendations for its revision and development of the new methodology for the revised SRP.

## 2. Evaluation Purpose and Objective

The purpose of IOM in commissioning this evaluation is to assess the process, results and effects of the SRP.  The evaluation will also serve to highlight reintegration best practices, lessons learned and recommendations for informing the key stakeholders and utilizing in future programming in this area.

## 3. Evaluation Scope

This proposed evaluation shall cover the implementation of the present SRP, starting from 1 January 2019 - until   the start date of the present evaluation.

Representative samples of beneficiaries (taking into account factors such as sex, age, region of return and country of destination) should be selected, participating in the SRP in various stages of the programme cycle and different periods - pre-COViD, during and after COViD, to understand COViD effect on the programme results.

The geographical scope of this evaluation covers all Georgia, considering that one of the criteria for stratification of the beneficiaries sample will be the geography of their return.

## 4. Evaluation Criteria

The SRP should be evaluated according to the following OECD-DAC criteria: relevance, coherence, effectiveness, efficiency, impact and sustainability.

## 5. Evaluation questions

Relevance

- To what extent is the SRP relevant and appropriate in relation to applicable national and international legal and policy frameworks and good standards?

- Are reintegration activities implemented under the SRP appropriately tailored to the needs (both immediate and longer term) and priorities of beneficiaries and their communities (including economic, social and psychosocial aspects)?

- Are the reintegration activities successfully selecting and targeting the most vulnerable beneficiaries and those where the assistance can have the most impact (e.g. how is vulnerability factored in beneficiary selection)?

- To what extent did the programme address specific reintegration needs of beneficiaries, including the most vulnerable and those with specific needs (including women, those living with disabilities, ethnic and other minorities, etc.) during its design and implementation?

- To what extent were local stakeholders and beneficiaries involved in the design, implementation and monitoring of the Programme activities?

Coherence

- To what extent is the SRP aligned and complementary with other reintegration activities implemented by other actors?  What is the added value, if any, of this programme compared to those other efforts?

- To what extent are the projects consistent with international norms and standards applicable in the same context?

Effectiveness

- To what extent was SRP assistance effective in improving the reintegration of returned migrants?

- What outcome/s has this intervention had on returnees and the host communities (positive/negative; intended/unintended).

- To what extent did the programme adapt to changing external conditions (i.e. COViD 19) to ensure its outcomes?

- What are the major factors influencing the achievement of the projects’ expected outcomes?

- To what extent was eligibility for assistance determined by vulnerabilities?

Efficiency

- How well were the resources (funds, expertise, and time) converted into results?

- To what extent was the assistance implemented/disbursed as scheduled?

- What challenges have been faced in the delivery of the SRP and how could implementation be improved (time, costs, human resources)?

- Is the volume and implementation capacity of the programme appropriate to the existing need?

- Does SRP have adequate monitoring and evaluation frameworks and practices to enable controlled management and evidence-based decision-making?

Impact

- To what extent do beneficiaries report sufficient levels of economic independence, social stability and psychosocial wellbeing in their communities of return? Does reintegration results differ for different groups (demographic, social, etc) of beneficiaries

- To what extent did the SRP assistance affect the migration plans of the beneficiaries?

- Is there a statistically significant difference in migration intentions and reintegration results between the programme beneficiaries and other returned migrants?

- To what extent can long-term changes be observed (whether intended or unintended, positive or negative)?

- Did the project take timely measures for mitigating any unplanned negative impacts (such as COVID and others)?

Sustainability

- What necessary structures, resources and processes are in place to ensure that benefits generated by the programme continue after the assistance cycle is over?

- To what extent were SRP beneficiaries able to sustain and amplify the benefit of the assistance provided?

- Is the programme supported by local institutions and well-integrated into local social and cultural structures?

- What are the major factors affecting sustainability, including any identified challenges faced by the implementing agency?

## 6. Evaluation methodology

The full evaluation methodology will be determined by IOM in close coordination with the selected service provider. As a minimum, the proposed methodology shall employ mixed methods and consist of the following components:

1. Desk review of the programme documentation (including the original description of the action, regular programme monitoring reports, the programme’s visibility outlets, other relevant documentation).

2. Surveys measuring reintegration sustainability and satisfaction. Sampling method and size for the quantitative data collection will be determined by the service provider in coordination with the evaluation manager. Potential option can be a stratified random sampling technique, with the sample calculated either as a % of total beneficiaries per reference period or a statistically representative sample of a confidence level of 95% and margin of error less than 5% per period.

3. In-depth semi-structured Key Informant Interviews (KIIs) with key stakeholders – senior staff of programme implementing agencies and other partners;

4. Focus Group discussions with programme beneficiaries and other returnees – including those registered with MOLHSA and not registered.

5. Observation of the programme’s sites (for example, activities that have been developed as a result of programme. Other sites to be identified).

## 7. Ethics, norms and standards for evaluation

IOM abides by the norms and standards of UNEG and expects all evaluation stakeholders to be familiar and comply with the UNEG’s  ethical conduct guidelines and  code of conduct .

## 8. Evaluation deliverables

The service provider should provide the following deliverables as part of this evaluation:

- Inception report including, at minimum, an Evaluation Matrix to demonstrate the service provider’s understanding of the ToR and outline data collection and analysis plans, as well as an indicative list of interviewees, focus group composition and respective guides; survey methodology and questionnaire/s; to be submitted to and reviewed by the Evaluation Manager prior to the field visit.

- Draft Evaluation Report to be submitted for review by the Evaluation Manager.

- Final Evaluation Report of maximum 30 pages (without annexes) in professional English language, including data visualization, incorporating feedback of the Evaluation Manager. The report should follow IOM defined style with minimum report content requirement are as follows:

- Cover page, list of acronyms.

- Table of contents.

- Executive summary.

- Methodology.

- Findings.

- Conclusions.

- Lessons learnt and best practices.

- Recommendations in order of priority.

- Annexes (list of interviewees, interview questionnaire/guides, etc.).

- A two-page Evaluation Brief following the IOM guidance and template, to provide a summary of key findings, Lessons learnt and best practices, conclusions and recommendations for easy sharing with IOM staff, donor, partners, and other stakeholders. The Evaluation brief should be submitted both in English and Georgian languages.

- Online debriefing for the key stakeholders on the evaluation results and lessons learnt.

## 9. Specifications of roles

The  service provider will be responsible for:

- Preparing for and carrying out data collection and analysis and delivering the products outlined above. The service provider will be responsible for leading the process and compiling the draft of each product.

- Providing periodic feedback as needed to the Evaluation Manager (Project Manager) on progress and any challenges faced.

- Organizing logistics during the field visit, including transportation, and interpretation services as needed.

- Providing a debrief at the end of the field visit (in country or a few days after the field visit) to present on the initial findings and tentative conclusions. This will allow for any obvious oversights, misinterpretations, or information gaps to be identified and addressed before the service provider begins drafting the full report.

- Drafting and revising the final report and evaluation brief, in coordination with the Evaluation Manager.

- Facilitating an online debriefing for the key project stakeholders to present conclusions of the evaluation and lessons learnt.

The Evaluation Manager (Project Manager) and the support team (project assistants and monitoring and evaluation officer) will be responsible for:

- Providing service provider with timely access to all relevant project documents and facilitating the initial preparations, including identifying relevant stakeholders and organizing the agenda.

- Arranging meetings with the stakeholders for data collection and lessons learnt debriefing.

- Managing the evaluation process. including feedback and comments to the evaluation matrix and draft evaluation report.

- Complete the management response to the evaluation to address issues or challenges flagged by the service provider.

## 10. Time Schedule

The evaluation is planned to be implemented in the period of June-November 2025. A precise timeline will be established with the selected service provider, and will consist of the following stages:

  - Planning and Desk Research Phase: Month 1

In the desk research phase, the relevant programme documents should be reviewed: the project proposals, the contracts, the relevant guidelines, reports.

Deliverable: The service provider will prepare and submit an inception report, including at minimum a detailed evaluation matrix, proposed evaluation methodology, an indicative list of interviewees and FGDs along with respective guides.

- Field Phase: Months 1-2

The service provider will carry out the assessment (indicatively 5 working days in Tbilisi and 2 in regions). The data will be collected according to the following methods:

- Briefing meeting with project management staff at the beginning of the Field Phase.

- In-depth interview with beneficiaries.

- Focus Group Discussions;

- Quantitative survey/s;

- Site visits/observations.

Deliverables: Debrief with the evaluation manager at end of the Field Phase (in person, or if needed remotely).

- Data processing and report drafting: Months 2-4

The service provider will process qualitative and quantitative data, draft and submit the report for IOM’s review. The draft evaluation report will be reviewed by the Evaluation Manager and relevant focal points of MoLHSA and feedback provided.

Deliverable: The service provider will submit the Draft Evaluation Report.

- Report finalization Phase: Months 5-6

This phase is mainly devoted to the finalization and submission of the final evaluation report, incorporating evaluation manager's feedback, and a two-page evaluation brief. Once the report is finalized, an online event will be organized for the key project stakeholders to present findings, lessons learnt, good practices and recommendations.

Deliverable: At the end of the phase a final report and evaluation brief will be delivered; a debriefing (possibly online) of the key stakeholders on evaluation findings, lessons learnt, good practices and recommendations.

Indicative calendar of the assignment:

| Activity | Working days | Responsible | Location | Months |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 |
| Desk review and development of Inception Report | 7 | service provider | Remote | x |  |  |  |  |  |
| Review of Inception Report | 10 | IOM |  | x |  |  |  |  |  |
| Field visit and data collection | 7 | service provider | On-site | x | x |  |  |  |  |
| Data processing, drafting and submission of draft report | 10 | service provider | Remote |  | x | x | x |  |  |
| Review of draft report and provision of feedback | 10 | IOM | Remote |  |  |  | x | x |  |
| Finalization of the report | 4 | service provider | Remote |  |  |  |  | x | x |
| Debriefing for the project stakeholders | 1 | service provider | Remote |  |  |  |  |  | x |

## 11. Evaluation Budget

IOM Georgia will identify a service provider in line with IOM’s procurement procedures to carry out the evaluation. The selected service provider will be expected to cover all evaluation-related expenses from the all-inclusive service fee, including travel costs, daily subsistence expenses, in-country transportation, interpretation/translation services, language editing, etc.

## 12. Evaluation requirements

Evaluation Team shall have international and national expertise. Lead experts of the evaluation team should meet the following minimum requirements:

- Advanced University degree in Social Sciences;

- At least 8 years of experience in leading and conducting development evaluations in the areas of institutional development, migration governance and migrant reintegration at international and national levels;

- In-depth knowledge of evaluation approaches, ability to apply both qualitative and quantitative data collection methods and to uphold high quality standards for evaluation as defined by UNEG;

- Ability to ensure ethics and integrity of the evaluation process, including confidentiality and the “do no harm” principle;

- Familiarity in UN results-based management (RBM) approach, gender equality, human rights-based approach in programming and evaluation;

- Ability to independently organize field visit in Georgia and mobilize needed support (driver, interpreter, etc.);

- Excellent written and spoken English and Georgian languages;

- Excellent report writing, communication and interviewing skills.

ANNEX 2: QUOTATION SUBMISSION FORM

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of their quotation along with Annex 3: Technical and Financial Offer. The Bidder shall fill in this form in accordance with the instructions indicated. No alterations to its format shall be permitted and no substitutions shall be accepted.

| Name of Bidder: | Click or tap here to enter text. |  |
| --- | --- | --- |
| RFQ reference: | Click or tap here to enter text. | Date: Click or tap to enter a date. |

VENDOR INFORMATION SHEET

BIDDER’S DECLARATION OF CONFORMITY

| Yes | No |  |
| --- | --- | --- |
| ☐ | ☐ | On behalf of the Supplier, I hereby represent and warrant that neither the Supplier, nor any person having powers of representation, decision-making or control over it or any member of its administrative, management or supervisory body, has been the subject of a final judgement or final administrative decision for one of the following reasons: bankruptcy, insolvency or winding-up procedures; breach of obligations relating to the payment of taxes or social security contributions; grave professional misconduct, including misrepresentation, fraud; corruption; conduct related to a criminal organisation; money laundering or terrorist financing; terrorist offences or offences linked to terrorist activities; child labour and other trafficking in human beings, any discriminatory or exploitative practice, or any practice that is inconsistent with the rights set forth in the Convention on the Rights of the Child or other prohibited practices; irregularity; creating or being a shell company. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier is financially sound and duly licensed. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier has adequate human resources, equipment, competence, expertise and skills necessary to complete the contract fully and satisfactorily, within the stipulated completion period and in accordance with the relevant terms and conditions. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier complies with all applicable laws, ordinances, rules and regulations. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier will in all circumstances act in the best interests of IOM. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that no official of IOM or any third party has received from, will be offered by, or will receive from the Supplier any direct or indirect benefit arising from the contract. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier has not misrepresented or concealed any material facts during the contracting process. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier will respect the legal status, privileges and immunities of IOM as an intergovernmental organization. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that neither the Supplier nor any persons having powers of representation, decision-making or control over the Supplier or any member of its administrative, management or supervisory body are included in the most recent Consolidated United Nations Security Council Sanctions List (the “UN Sanctions List”) or are the subject of any sanctions or other temporary suspension. The Supplier will immediately disclose to IOM if it or they become subject to any sanction or temporary suspension. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier does not employ, provide resources to, support, contract or otherwise deal with any person, entity or other group associated with terrorism as per the UN Sanctions List and any other applicable anti-terrorism legislation. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that, the Supplier will apply the highest ethical standards, the principles of efficiency and economy, equal opportunity, open competition and transparency, and will avoid any conflict of interest. |
| ☐ | ☐ | On behalf of the Supplier, I further represent and warrant that the Supplier undertakes to comply with the Code of Conduct, available at https://www.ungm.org/Public/CodeOfConduct. |
| ☐ | ☐ | It is the responsibility of the Supplier to inform IOM immediately of any change to the information provided in this Declaration. |
| ☐ | ☐ | On behalf of the Supplier, I certify that I am duly authorized to sign this Declaration and on behalf of the Supplier I agree to abide by the terms of this Declaration for the duration of any contract entered into between the Supplier and IOM. |
| ☐ | ☐ | IOM reserves the right to terminate any contract between IOM and the Supplier, with immediate effect and without liability, in the event of any misrepresentation made by the Supplier in this Declaration. |

Signature:

Name: 	Click or tap here to enter text.

Title:	Click or tap here to enter text.

Date:  	Click or tap to enter a date.

## ANNEX 3: TECHNICAL AND FINANCIAL OFFER - SERVICES

Bidders are requested to complete this form, sign it and return it as part of their quotation along with Annex 2 Quotation Submission Form. The Bidder shall fill in this form in accordance with the instructions indicated. No alterations to its format shall be permitted and no substitutions shall be accepted.

| Name of Bidder: | Click or tap here to enter text. |  |
| --- | --- | --- |
| RFQ reference: | Click or tap here to enter text. | Date: Click or tap to enter a date. |

Technical Offer

Provide the following:

- a brief description of your qualification, capacity and expertise that is relevant to the Terms of Reference.

- a brief methodology, approach and implementation plan;

- team composition and CVs of key personnel

Financial Offer

Provide a lump sum for the provision of the services stated in the Terms of Reference of your technical offer. The lump-sum should include all costs of preparing and delivering the Services. All daily rates shall be based on an eight-hour working day.

Currency of Quotation: Click or tap here to enter text.

| Ref | Description of Deliverables | Price |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |
| 3. |  |  |
| 4. |  |  |
| 5. |  |  |
| Total Price |  |  |

Breakdown of Fees

| Personnel / other elements | UOM | Qty | Unit Price | Total Price |
| --- | --- | --- | --- | --- |
| Personnel |  |  |  |  |
| e.g. Project Manager/Team Leader | day |  |  |  |
| Other expenses |  |  |  |  |
| International flights |  |  |  |  |
| Subsistence allowance |  |  |  |  |
| Local Transportation |  |  |  |  |
| Communication |  |  |  |  |
| Other Costs: (please specify) |  |  |  |  |
| Total |  |  |  |  |

Compliance with Requirements

|  | You Responses |  |  |
| --- | --- | --- | --- |
|  | Yes, we will comply | No, we cannot comply | If you cannot comply, pls. indicate counter proposal |
| Delivery Lead Time | ☐ | ☐ | Click or tap here to enter text. |
| Validity of Quotation | ☐ | ☐ | Click or tap here to enter text. |
| Payment terms | ☐ | ☐ | Click or tap here to enter text. |
| Other requirements [pls. specify] | ☐ | ☐ | Click or tap here to enter text. |

| I, the undersigned, certify that I am duly authorized to sign this quotation and bind the company below in event that the quotation is accepted. |  |
| --- | --- |
| Exact name and address of company Company NameClick or tap here to enter text. Address: Click or tap here to enter text. Click or tap here to enter text. Phone No.: Click or tap here to enter text. Email Address: Click or tap here to enter text. | Authorized Signature: Date: Click or tap here to enter text. Name: Click or tap here to enter text. Functional Title of Authorised Signatory: Click or tap here to enter text. Email Address: Click or tap here to enter text. |

https://georgia.iom.int/sites/g/files/tmzbdl1311/files/iom_reintegration-outcomes-georgia-study-june-2021.pdf

https://migration.commission.ge/files/mra_liaflet_eng.pdf

Vendor Information Sheet.xlsx

This form is mandatory to fill in and sign by every vendor who submits quotation