REQUEST FOR PROPOSAL

Date: 11 July 2017

UNICEF Tbilisi requests proposals Community Mobilization for the Multiple Indicator Cluster Survey (MICS)

in the regions of Georgia

Submit your proposal with unit price(s) in GEL together with vendor registration form, as instructed, on or before closing time.

- Note that failure to submit proposal in GEL, or in accordance with the requested terms, will result in automatic invalidation of your application.

- In addition, please note that:

- UNICEF and its implementing partners are VAT exempt. Kindly ensure that all price(s) quoted in GEL are excluding VAT;

- For transparency of the process we require that the proposals are received in the sealed form (sealed envelopes);

- It is important that you read all of the provisions, to ensure that you understand UNICEF’s requirements and can submit an offer in compliance with them. This includes submission of ALL documents requested. Note that your proposals should be submitted in English using the enclosed format. Proposals received in any other manner or after the indicated above deadline will be INVALIDATED.

- Evaluation criteria will be based on reliability of the organization, suggested methodology and approach, best price and proposal terms. The ratio between the technical and price criteria is 70:30.

- In case of pre-payment request, bank guarantee letter should be submitted

SUBMISSION TERMS:

In order to be considered for an award, your technical and price proposals should be hand delivered in separate sealed envelopes and placed in the locked Tender Box located at the Ground Floor of UN House, 9 Eristavi Street, Vake, Tbilisi 0179, Georgia NO LATER than 15:00 of 23 July 2018.

While the price proposals remain sealed until the technical evaluation is completed, the technical envelopes will be opened immediately after the closing time and forwarded to the unit designated to manage the selection process. One representative from each bidding company may attend the opening process.

The sealed envelopes should be labeled as follows: (1) P-GEO- 9141194-009 Technical Proposal and (2)  P-GEO- 9141194-009- Price Proposal.

Technical Proposal should include:

Company’s profile; Project proposal; Description of the proposed work plan, timeline, and working methodology; CV s of suggested experts;

Price Proposal should include:  Cover letter; proposed budget with indication of proposed fees; (in GEL).

Please, do not hesitate to contact us if you have any questions, contact persons: Nino Dzotsenidze at ndzotsenidze@unicef.org and Sofia Chaava at schaava@unicef.org or at 2251130 # 229.

Respectfully,

Vakhtang Akhaladze

Operations Manager, UNICEF Tbilisi

Community Mobilization for the Multiple Indicator Cluster Survey (MICS)

in the regions of Georgia

Terms of Reference

Background

Developed and supported by UNICEF, MICS (Multiple Indicator Cluster Survey) is one of the largest international household survey programmes worldwide. It is designed to collect estimates of key indicators that are used to assess the situation of children and women.

As part of the global effort to further develop national capacities to generate and analyze high quality and disaggregated data, UNICEF launched the sixth round of MICS in October 2016 – specifically designed to meet policy-makers’ needs in the Sustainable Development Goal (SDG) era.

Sixth round of MICS in Georgia is being launched in 2018 and the final results will be available in 2019. MICS in Georgia is conducted by GeoStat with the technical support and partial financial assistance of UNICEF and partners.

The MICS in Georgia aims to support the generation of high quality and internationally comparable data about women and children in various areas to strengthen evidence-based planning and informed decision-making for the implementation of the Convention on the Rights of the Child (CRC), the EU association Agenda and Action Plan, National Human Rights strategy and Action plan, as well as recently developed/nationalized SDGs. By providing disaggregated data, the Georgia MICS will identify disparities amongst different groups, in order to facilitate policy-making aimed at increasing the social inclusion of women and children who are in the most vulnerable situations.

Lead testing will also be carried out within the framework of the MICS survey in Georgia defining levels of lead in children’s blood and providing key evidence for taking appropriate regulatory, policy, inspection, market surveillance and other public health related measures aimed at preventing and eradicating lead poisoning in Georgia.

Desired Outcomes of MICS:

- Evidence is available to inform policy and legislation on children;

- Government has policies, legislation and budgets that respond to the needs of children as identified by MICS;

- Children are higher on the national development agenda;

- Children’s rights are high on public agenda.

Purpose of Assignment for the communication organization:

UNICEF wants to select NGO/network of CSOs to support in social mobilization about MICS to raise awareness among public in the selected regions through inter-personal communication and community dialogues.

Audiences

- General public, civil society

Strategic Objectives of the Campaign:

- Organize community meetings and mobilize public support in the selected communities to raise awareness about the MICS field work and to increase cooperation from public during the process.

Specific tasks:

| Task | Description | Time Period | Quantity |
| --- | --- | --- | --- |
| To conduct face to face meetings and communication with households in the 10 regions to provide information and to distribute flyers (will be provided by UNICEF) | Ajara Guria Imereti Kakheti Mtskheta-Mtianeti Racha-lechkhumi and kvemo svaneti Samegrelo Zemo-Svaneti Samtskhe Javakheti Qvemo Kartli Shida Kartli | September 1 – November 15, 2018 | Number of meetings in the selected villages of the 10 regions will be established according to the field work calendar provided by GeoStat. |
| Organize town hall meetings in the regional centers | Ajara Guria Imereti Kakheti Mtskheta-Mtianeti Racha-lechkhumi and kvemo svaneti Samegrelo Zemo-Svaneti Samtskhe Javakheti Qvemo Kartli Shida Kartli | September, 2018 | 10 |
| Organize meetings with community leaders (teachers, doctors, civil society members) to spread the word about MICS to ensure smooth cooperation from public. | Ajara Guria Imereti Kakheti Mtskheta-Mtianeti Racha-lechkhumi and kvemo svaneti Samegrelo Zemo-Svaneti Samtskhe Javakheti Qvemo Kartli Shida Kartli | September 1 – November 15, 2018 | 10 |

Deliverables

- Detailed action plan with the planned meetings and timeline;

- Meetings organized and social mobilization conducted;

- Final report.

Qualifications:

- Minimum of 5 years of experience in developing community mobilization strategies.

- Extensive contacts in civil society organizations in the regions of Georgia

- Experience in organizing town-hall meetings, community gatherings, media events

- Strong monitoring and evaluation capacity.

- Attentiveness to detail and compliance with timelines.

- Excellent report writing skills in English and Georgian.

Timeline and milestones:

| Development of the detailed plan of action | 17 August, 2018 |
| --- | --- |
| Carrying out the plan with meetings and community mobilization | September 1 – November 15, 2018 |
| Final report | December 2018 |

Supervision

The work of the organization will be directly supervised and guided by UNICEF Communication Officer in consultation with Social Policy Section.

Duration:

All the deliverables till December 2018.

# Text boxes

Please quote RFP# P-GEO- 9141194-009 in all future correspondences on this matter.